## Management
Group Members | Role | Febuary (10-28) | March (1-14) | March (15-31) | April (1-15) | April (16-30) | May (1-15) | May (16-31) | June
Berk Yalçınkaya | Project Manager | * Define project scope * Document requirements * Create 8-week sprint roadmap | * Track tasks and progress * Prepare weekly report | * Project Manager * Coordinate testing process | * Review sprint progress | * Ensure requirements alignment | * Collect usability feedback | * Organize full system testing | * Prepare final documentation * Organize presentation
Hıdır Işıkbaş | Backend Developer | * Design application architecture * Plan service layer structure * Define API integration strategy | * Implement UserService skeleton * Develop API client structure | * Complete initialize() and refreshFromApi() methods | * Add validation logic | * Identified the necessary classes and methods. | *Improve naming conventions & clean code | * Refactor code * Fix edge cases | * Prepare production build
Asya Yayla | Risk Manager | * Identify technical risks (API failure, data loss, etc.) * Prepare risk matrix | * Test API connectivity * Review data persistence risks | * Test API failure scenarios | * Analyze invalid data entry risks | * Evaluate data conflict risks | * Analyze accidental deletion risk | * Conduct final risk assessment * Check for critical vulnerabilities | * Perform live environment risk analysis * Approve release
Burak Bayraktar | Database Developer | * Design User data model * Define LocalStorage data structure | * Implement LocalStorage data source * Develop read/write functions | * Test BrandEntity and car table synchronization | * Test CRUD operations | * Test data consistency after updates | * Verify DataBase and tables consistency after deletion | * Perform data integrity testing | * Test data persistence in production
Hasan Eren Ertekin | Backend Developer | *Design entity models (Car, Brand, BaseEntity) *Define Car–Brand relationship (1-N) | *Implement DTO structure (AddCarDto, AddBrandDto) *Setup EF Core migrations *Configure Swagger for API testing | *Implement Brand entity and table *Resolve foreign key & migration conflicts | *Implement Brand CRUD endpoints | *Test API via Swagger | *Refactor controllers and DTO usage | *Final API testing | *Prepare backend documentation

## Budget
Period | Active Members | Duration (days) | Total Cost ($)
Febuary (10-28) | 5 | 19 | 11305
March (1-14) | 5 | 14 | 8330
March (15-31) | 5 | 17 | 10115
April (1-15) | 5 | 15 | 8925
April (16-30) | 5 | 15 | 8925
May (1-15) | 5 | 15 | 8925
May (16-31) | 5 | 16 | 9520
June | 5 | 15 | 8925