## Management
Group Members | Role | Febuary (10-28) | March (1-14) | March (15-31) | April (1-15) | April (16-30) | May (1-15) | May (16-31) | June
Berk Yalçınkaya | Project Manager | * Define project scope * Document requirements * Create 8-week sprint roadmap | * Track tasks and progress * Prepare weekly report | * Project Manager * Coordinate testing process | * Review sprint progress | * Ensure requirements alignment | * Collect usability feedback | * Organize full system testing | * Prepare final documentation * Organize presentation
Hıdır Işıkbaş | Frontend Developer | * UI/UX plan (Catalog, Detail, Auth, Admin) * Set up React routing & component structure * Define frontend API services & auth flow | * Build Login/Register UI + validation * Protected routes (catalog requires login) * Base layout (navbar/footer, responsive) | * Catalog UI (cards, filters, sorting) * Connect Catalog to API * Car Detail UI (gallery, specs) | * Favorites UI (add/remove, list) * Contact Form UI + submit flow * Loading/error states & state management | * Admin UI (car add/edit forms) * Image upload + delete UI * Brand management CRUD screens | * Responsive + accessibility improvements * Styling consistency (components) * Price history/notify settings UI (if scope) | * End-to-end integration fixes * Edge cases + empty states * Usability feedback fixes | * Frontend production build * Frontend docs (setup/build/env) * Support final demo/presentation
Asya Yayla | Risk Manager | * Identify technical risks (API failure, data loss, etc.) * Prepare risk matrix | * Test API connectivity * Review data persistence risks | * Test API failure scenarios | * Analyze invalid data entry risks | * Evaluate data conflict risks | * Analyze accidental deletion risk | * Conduct final risk assessment * Check for critical vulnerabilities | * Perform live environment risk analysis * Approve release
Burak Bayraktar | Database Developer | * Design User data model * Define LocalStorage data structure | * Implement LocalStorage data source * Develop read/write functions | * Test BrandEntity and car table synchronization | * Test CRUD operations | * Test data consistency after updates | * Verify DataBase and tables consistency after deletion | * Perform data integrity testing | * Test data persistence in production
Hasan Eren Ertekin | Backend Developer | *Design entity models (Car, Brand, BaseEntity) *Define Car–Brand relationship (1-N) | *Implement DTO structure (AddCarDto, AddBrandDto) *Setup EF Core migrations *Configure Swagger for API testing | *Implement Brand entity and table *Resolve foreign key & migration conflicts | *Implement Brand CRUD endpoints | *Test API via Swagger | *Refactor controllers and DTO usage | *Final API testing | *Prepare backend documentation

## Budget
Period | Active Members | Duration (days) | Total Cost ($)
Febuary (10-28) | 5 | 19 | 11305
March (1-14) | 5 | 14 | 8330
March (15-31) | 5 | 17 | 10115
April (1-15) | 5 | 15 | 8925
April (16-30) | 5 | 15 | 8925
May (1-15) | 5 | 15 | 8925
May (16-31) | 5 | 16 | 9520
June | 5 | 15 | 8925

## CarGallery_Week2
CarGallery Strategic and Technical Overview
Presentation-ready summary for project management review and final deck support
No | Section | Focus Area | Key Message | CarGallery-Specific Notes
1 | Executive Summary | Business / Product | What it is and why it matters. | CarGallery is a dealership catalog + admin system. Admins manage cars/brands/images/users; registered customers browse, favorite, and send contact requests.
2 | Product Description and Vision | Business / Product | Users, problem, and growth vision. | For dealership staff and registered customers. Replaces spreadsheet tracking with searchable listings and a scalable engagement platform.
3 | Core Features and Capabilities | Business / Product | MVP + planned capabilities. | MVP: auth, catalog, filters, car details, admin car/brand/user CRUD, image upload. Planned: block guests, favorites, price history + alerts, contact request workflow.
4 | Technical Architecture and Infrastructure | Architecture / Security | System structure and hosting. | React (Vite) client calls ASP.NET Core Web API over HTTPS. Relational DB (SQLite dev; Postgres/MySQL ready); images stored on server/object storage.
5 | Technology Stack | Architecture / Security | Frameworks, database, tooling. | Frontend React + TypeScript; Backend ASP.NET Core + EF Core; DB SQLite. Tooling: Git, Swagger/Postman; CI-ready scripts.
6 | Security Architecture | Architecture / Security | How data and actions are protected. | HTTPS, hashed passwords, server-side JWT validation, RBAC on endpoints. Input validation, secure uploads, and admin action logs.
7 | Role and Authorization Management Model | Architecture / Security | Roles and permissions model. | Roles: Customer, Admin, Super Admin. Enforce access in the API (and UI) with least-privilege policies per endpoint.
8 | Clearance Level System | Architecture / Security | Access levels mapped to features. | Clearance: L0 guest (no catalog), L1 registered (view), L2 engaged (favorites/contact), L3 admin (manage), L4 super admin (role/security).
9 | User Experience and Interface | UX / Operations | Main screens and user flow. | Pages: login/register, catalog (search/filter/sort), car detail (gallery/specs), favorites/price tracking/contact (planned), admin panel (cars/brands/users). Responsive UI with clear feedback.
10 | Installation and Deployment | UX / Operations | How to run and deploy. | Local: run API + Vite, migrate/seed DB, set env vars. Deploy: build frontend, host API, configure prod DB/secrets/HTTPS, enable backups.
11 | Integration and Scalability | UX / Operations | Integrations and scaling approach. | Integrate email/SMS for alerts, analytics, and storage. Scale with pagination, caching, background jobs, and a production DB.
12 | Competitive Analysis and Differentiation | Strategy / Requirements | Differentiators vs alternatives. | More structured than social listings and safer than spreadsheets: access control, consistent data, and engagement tools (favorites/alerts/contact).
13 | Licensing and Commercial Model | Strategy / Requirements | Commercialization approach. | Academic prototype; can evolve into white-label SaaS with tiered subscriptions and add-ons (integrations, analytics, multi-branch).
14 | Technical Requirements | Strategy / Requirements | Non-functional requirements. | NFRs: fast catalog with pagination, secure auth/RBAC/uploads, logging + backups, maintainable code, basic tests and monitoring.
Color Guide: Business / Product = orange, Architecture / Security = blue, UX / Operations = green, Strategy / Requirements = yellow
Note on E6: Prepared as a presentation-friendly overview sheet for the CarGallery project.

## CarGallery_Week3
CarGallery Risk Management, Testing & Success Criteria
Week 3 package: risk register + matrix, security/privacy controls, roadmap, validation/testing plan, and measurable success criteria
1)Risk Assesment and Management
|  | Category | Risk Id
|  | Security | S1
|  | Performance | P1
|  | Database & Data Integrity Risks | D1
2) Risk Matrix
| Impact (1 = Low, 5 = Very High) | [5 empty] | Legend
|  | 1 | 2 | 3 | 4 | 5 | Low (1–4)
Probability (1=Low 5=Very High) | 5 | 5 | 10(S6,D2,D8,D12) | 15(S2,S5,S12,D5) | 20(S1,S4) | 25 | Medium (5–9)
| 4 | 4 | 8(P7,S8,S9,S10,D6) | 12(P2,P3,P4,P8,S3,S7,D1,D4) | 16(P1) | 20(S1,S4) | High (10–15)
| 3 | 3 | 6(P9,P12,D11) | 9(P5,P6,P10,P11,S11,D3,D7,D9,D10) | 12(P2,P3,P4,P8,S3,S7,D1,D4) | 15(S2,S5,S12,D5) | Critical (16–25)
| 2 | 2 | 4 | 6(P9,P12,D11) | 8(P7,S8,S9,S10,D6) | 10(D2,D8,D12)
| 1 | 1 | 2 | 3 | 4 | 5
3) Performance Issues – Detailed Risk Analysis
Risk ID | Risk Name | Detailed Explanation | Probability (1–5) | Impact (1–5) | Score | Risk Level | Mitigation Strategy
P1 | Slow catalog loading with many cars | If the number of cars in the database increases significantly, loading all cars at once may slow down the catalog page and increase server response time. | 4 | 4 | 16 | Critical | Implement pagination and lazy loading
P2 | Large image files slow down the website | High-resolution images uploaded for cars may increase page load time and reduce user experience performance. | 4 | 3 | 12 | High | Use image compression and thumbnails
P3 | Missing database indexes | If important database fields such as BrandId, GalleryId, or CityId are not indexed, search and filtering operations will become slower. | 3 | 4 | 12 | High | Add database indexes
P4 | Increased API response time with more users | When multiple users access the system simultaneously, the API response time may increase and affect system performance. | 3 | 4 | 12 | High | Implement caching mechanisms
P5 | Performance issues with many galleries | As the number of galleries grows, queries that retrieve gallery-related data may take longer to execute. | 3 | 3 | 9 | Medium | Optimize database queries
P6 | Inefficient filtering and search operations | Poorly optimized filtering and search logic may cause unnecessary database load and slower responses. | 3 | 3 | 9 | Medium | Optimize query structure
P7 | Server storage overload due to many images | Uploading a large number of images may consume server storage and affect system performance over time. | 2 | 4 | 8 | Medium | Implement storage monitoring and limits
P8 | SQLite limitations with large datasets | SQLite may not perform well when the dataset becomes very large or when many concurrent requests occur. | 3 | 4 | 12 | High | Plan migration to a scalable database (PostgreSQL/MySQL)
P9 | No CDN usage for images | Without a Content Delivery Network (CDN), images are served from a single server which may slow down performance for users. | 2 | 3 | 6 | Medium | Use CDN or cloud storage
P10 | High memory usage on backend services | Backend services may consume excessive memory when processing large requests or large datasets. | 3 | 3 | 9 | Medium | Optimize service logic
P11 | Too many repeated requests from users | Some users may send too many requests (refreshing or automated requests), which can affect system performance. | 3 | 3 | 9 | Medium | Implement rate limiting
P12 | Frontend performance issues on low-end devices | Users with older devices or slower hardware may experience slow UI rendering and lagging interactions. | 2 | 3 | 6 | Medium | Optimize frontend components
3.1)Security Risks – Detailed Risk Analysis
Risk ID | Risk Name | Detailed Explanation | Probability (1–5) | Impact (1–5) | Score | Risk Level | Mitigation Strategy
S1 | RBAC not properly enforced | If role-based access control is not implemented correctly, non-admin users may access admin endpoints and perform unauthorized operations. | 4 | 5 | 20 | Critical | Enforce strict RBAC policies on all API endpoints
S2 | JWT token theft | If tokens are stolen through insecure storage or network interception, attackers may impersonate legitimate users. | 3 | 5 | 15 | High | Use HTTPS, short-lived tokens, and refresh tokens
S3 | Brute force login attacks | Attackers may try many password combinations to gain access to user accounts. | 3 | 4 | 12 | High | Implement rate limiting and account lockout
S4 | Unauthorized admin API access | Some API endpoints might be accessible without proper authorization checks. | 4 | 5 | 20 | Critical | Use authorization middleware and role validation
S5 | Malicious file uploads | Attackers may upload harmful files disguised as images which could affect the server or system. | 3 | 5 | 15 | High | Validate file types and restrict uploads
S6 | SQL Injection vulnerability | Improper input validation may allow attackers to manipulate database queries and access sensitive data. | 2 | 5 | 10 | High | Use parameterized queries and ORM protection
S7 | Cross-Site Scripting (XSS) | Attackers may inject malicious scripts into forms or input fields that execute in other users' browsers. | 3 | 4 | 12 | High | Sanitize and validate all user inputs
S8 | Cross-Site Request Forgery (CSRF) | Attackers may trick authenticated users into performing unwanted actions in the system. | 2 | 4 | 8 | Medium | Implement CSRF protection tokens
S9 | Token replay attacks | An attacker may reuse a captured authentication token to access the system again. | 2 | 4 | 8 | Medium | Use token expiration and token rotation
S10 | Sensitive information exposed in logs | Logs may contain sensitive data such as tokens, user details, or system information that could be exploited. | 2 | 4 | 8 | Medium | Secure and sanitize logging mechanisms
S11 | Weak password policy | Users may create weak passwords, making accounts easier to compromise. | 3 | 3 | 9 | Medium | Enforce strong password requirements
S12 | Cross-gallery data access vulnerability | If GalleryId filtering is not enforced properly, users may access data from other galleries. | 3 | 5 | 15 | High | Enforce gallery-level data isolation in APIs
3.2)Database & Data Integrity Risks – Detailed Risk Analysis
Risk ID | Risk Name | Detailed Explanation | Probability (1–5) | Impact (1–5) | Score | Risk Level | Mitigation Strategy
D1 | Database migration failure | During schema updates or migrations, errors may occur that prevent the database from updating correctly or may break the application. | 3 | 4 | 12 | High | Test migrations in staging environment before production
D2 | Data corruption | Unexpected system failures, bugs, or incorrect operations may corrupt stored data in the database. | 2 | 5 | 10 | High | Implement regular backups and integrity checks
D3 | Duplicate records in database | Without proper constraints, duplicate cars, brands, or users may be stored in the system. | 3 | 3 | 9 | Medium | Add unique constraints and validation rules | Notes / Dependencies
D4 | Orphan records | Deleting related records without proper foreign key constraints may leave orphan records in the database. | 3 | 4 | 12 | High | Use foreign keys and cascade rules | Required for next week
D5 | Incorrect GalleryId mapping | Cars, brands, or users may be assigned to the wrong gallery if GalleryId validation is missing. | 3 | 5 | 15 | High | Validate GalleryId in all CRUD operations | Reduces R1/R2/R3
D6 | Backup failure or missing backups | If backups are not performed regularly, important data may be lost permanently. | 2 | 4 | 8 | Medium | Schedule automated backups | Timebox to avoid scope creep
D7 | Schema conflicts during team development | Multiple developers working on database models may create conflicting schema changes. | 3 | 3 | 9 | Medium | Use version-controlled migrations | If alerts out-of-scope: document as future work
D8 | Data loss during deployment | Deployments may accidentally overwrite or remove existing database data. | 2 | 5 | 10 | High | Prepare rollback plans before deployment | Staging run-through before demo
D9 | Invalid image file paths stored in database | Uploaded image paths may become invalid if files are moved or deleted improperly. | 3 | 3 | 9 | Medium | Validate and manage file storage correctly
D10 | JSON data structure errors | Incorrect JSON formatting (e.g., ImageUrls list) may cause data retrieval problems. | 3 | 3 | 9 | Medium | Validate JSON fields before saving
D11 | Database growth affecting performance | As the number of cars, users, and galleries increases, the database size may grow and affect performance. | 2 | 3 | 6 | Medium | Implement data archiving and indexing
D12 | Unauthorized database access | If database credentials are exposed or poorly protected, attackers may access sensitive data. | 2 | 5 | 10 | High | Secure environment variables and restrict DB access
4) Implementation Roadmap (March–June)
Phase / Timebox | Goal | Key Deliverables |  |  |  |  | Owner(s)
Week 3 (next week) | Weekly submission package | Complete missing doc sections; risk register + matrix; security/privacy checklist; testing plan; success criteria; update Jira/board |  |  |  |  | Berk + Asya
March | Security baseline & access control | JWT validation; RBAC on endpoints; protect catalog for guests; upload constraints; error handling |  |  |  |  | Hasan + Hıdır
April | Engagement workflow | Favorites + contact request flow; admin review page; UI polish; DB updates |  |  |  |  | Hıdır + Hasan + Burak
May | Alerts + quality gate | Price history; notification stub; pagination/perf; usability tests; bug fixes |  |  |  |  | Hasan + Berk
June | Release & final presentation | Deployment guide; final E2E testing; backup plan; final slides + rehearsal |  |  |  |  | Berk + Team
5) Success Criteria (How we determine project success)
Category | Success Criterion | Target | How Measured / Evidence
Security | Admin endpoints protected by server-side RBAC | Non-admin receives 403; admin succeeds | API tests showing 401/403 + successful admin actions
Access Control | Guests cannot view catalog | Guest redirected to login; API returns 401/403 | Demo: open catalog as guest → blocked
Functionality | Admin can add/edit/delete cars + manage brands | All CRUD flows work without errors | Demo checklist + screenshots
Media Handling | Image upload/delete works safely | Only allowed types; size limit enforced | Upload tests + stored file path evidence
Quality | Test plan executed | ≥ 90% planned test cases passed; no P0 bugs | Test checklist with pass/fail summary
Performance | Catalog endpoint responsive | Paged listing returns within target (e.g., <1s on test env) | Timing logs / perf notes
Documentation | Deployment + usage documented | README + deployment checklist complete | Docs in repo + instructor review
Project Management | Plan delivered to June with weekly tracking | Updated management sheet + weekly reports | Excel management table + Jira board snapshots
Week 3 Update: Validation & Testing Plan (City + Multi-Gallery)
Test type | What we validate | Tools/Method | Owner | Week(W) | Pass criteria
Unit tests (API) | GalleryId scoping, role checks, input validation. | xUnit + EF InMemory/Test DB | Backend | W5–W6 | All critical tests pass, coverage on core endpoints.
Integration tests | City→gallery endpoints + gallery-scoped catalog; negative leakage tests. | Postman/Newman or TestServer | Backend | W6 | No cross-gallery access; correct status codes.
Frontend E2E smoke | City select → gallery select → catalog → detail. | Playwright/Cypress | Frontend | W6 | Happy path completes without errors.
UX validation | Users can reach a car detail within 30s after city selection. | 5-user quick test + notes | PM+FE | W6 | ≥80% complete task; issues logged.
Performance check | Gallery list + catalog response time with pagination. | k6/JMeter quick run | Backend | W7 | p95 < 1.5s on test env (target).